## Option 1
No. | Task | Effort (hours) | Resource | Start Date | End Date | Note
1 | Training/self study business requirement and practise | 12 | Senior Tester | 2017-02-23 | 2017-02-24
2 | Setup local test environments | 8 | Senior Tester | 2017-02-24 | 2017-02-27 | Setup at local testing side, excluding setup test servers which will be done at client side
3 | Create test strategy/test plan document | 12 | Senior Tester | 2017-02-27 | 2017-02-28 | Create, review, approve
4 | Test data preparation | 26 | Nam | 2017-03-06 | 2017-03-10 | 30 Tenants, 2500/3000 users, 300000 timesheets, 300000 expenses, 3000 projects, 6000 tasks, 3000 Sale proposals, 6000 lines, 3000 contacts.
5 | Create test case | 4.8 | Senior Tester | 2017-03-01 | 2017-03-01 | Test happy case only
6 | Implement performance test script | 60 | Senior Tester | 2017-03-02 | 2017-03-13 | Support by Tester Leader
7 | Execute Load Test | 15 | Senior Tester | 2017-03-14 | 2017-03-15 | 6 rounds with each 2 hours (constraint of tool, does not allow to run 1 round 12 hours), Monitor hardware usage, Collect report between loads.
8 | Analyse, report | 2 | Senior Tester | 2017-03-16 | 2017-03-16 | First test report available
9 | Investigate bottle neck | 8 | Senior Tester | 2017-03-17 | 2017-03-17 | Both developer and tester take part in to this task (each takes 4 hours).
10 | Restore DB and run script to create test data | 2 | Senior Tester | 2017-03-20 | 2017-03-20 | Reuse script
11 | Execute Load Test (retest) | 15 | Senior Tester | 2017-03-20 | 2017-03-22 | 6 rounds with each 2 hours (constraint of tool, does not allow to run 1 round 12 hours), Monitor hardware usage, Collect report between loads.
12 | Analyse, report | 2 | Senior Tester | 2017-03-22 | 2017-03-22 | Final test report available after fixing issues
| Groups | Functions | Percentage (%)
| Most access | Home | 35
Login
| Most access to add | Add Timesheet | 35
Add Expense
| Common access to approve | Approve Timesheet | 7
Approve Expense
| Common access to add | Add contact | 10
Add sale proposal
| Common access to add invoice | Add invoice for contact | 10
Add invoice for Sale proposal
Add invoice for Project with Task
Add invoice for Project with Timesheet and Expense
| Rarely access | Add reminder | 3
| Groups | Functions | Percentage (%)
| Normal users | Home | 80%
Login
Add contact
Add sale proposal
Add Timesheet
Add Expense
Add reminder
Add note
| Admin users | Home | 20%
Login
Approve Timesheet
Approve Expense
Add invoice for contact
Add invoice for Sale proposal
Add invoice for Empty project
Add invoice for Project with Task
Add invoice for Project with Timesheet and Expense
|  |  |  | No | Deliverable | Effort (hours)
|  |  |  | 1 | Preparation. | Make sure the testing scripts have been implemented. RHINO websites is accessible. Nobody access to the site.
Testing team must have permission to monitor the hardware usage of the test servers while testing.
Testing team must have Blazemeter license.
|  |  |  | 2 | Generates and load 2.500 users (ram up from 100) send requests to defined functions within 12 hours. | Simulate 2.500 simultaneous users accessing to defined functions to determine if the system still handle the load with the expected performance.
|  |  |  | 3 | Complete running the script and return a test result | Returns an approximately loading time for all functions which have been run. Or any error message returned while testing running. Analyse and point out where the bottleneck or root causes of the performance issues.
|  |  |  | No | Deliverable | Effort (hours)
|  |  |  | Normal users | Home | 80%
Login
Add contact
Add sale proposal
Add Timesheet
Add Expense
Add reminder
Add note
|  |  |  | Admin users | Home | 20%
Login
Approve Timesheet
Approve Expense
Add invoice for contact
Add invoice for Sale proposal
Add invoice for Empty project
Add invoice for Project with Task
Add invoice for Project with Timesheet and Expense

## Option 2
No. | Task | Effort (hours) | Resource | Start Date | End Date | Note
1 | Training/self study business requirement and practise | 12 | Senior Tester | 2017-02-23 | 2017-02-24
2 | Setup local test environments | 8 | Senior Tester | 2017-02-24 | 2017-02-27 | Setup at local testing side, excluding setup test servers which will be done at client side
3 | Create test strategy/test plan document | 12 | Test Leader | 2017-02-23 | 2017-02-24 | Create, review, approve
4 | Test data preparation | 26 | Nam | 2017-03-03 | 2017-03-08 | 30 Tenants, 2500/3000 users, 300000 timesheets, 300000 expenses, 3000 projects, 6000 tasks, 3000 Sale proposals, 6000 lines, 3000 contacts.
5 | Create test case | 4.8 | Test Leader | 2017-02-27 | 2017-02-27 | Test happy case only
6 | Implement performance test script | 60 | Senior Tester | 2017-02-27 | 2017-03-08 | Support by Tester Leader
7 | Execute Load Test | 15 | Senior Tester | 2017-03-09 | 2017-03-10 | 6 rounds with each 2 hours (constraint of tool, does not allow to run 1 round 12 hours), Monitor hardware usage, Collect report between loads.
8 | Analyse, report | 2 | Senior Tester | 2017-03-10 | 2017-03-10 | First test report available
9 | Investigate bottle neck | 8 | Senior Tester | 2017-03-13 | 2017-03-13 | Both developer and tester take part in to this task (each takes 4 hours).
10 | Restore DB and run script to create test data | 2 | Senior Tester | 2017-03-14 | 2017-03-14 | Reuse script
11 | Execute Load Test (retest) | 15 | Senior Tester | 2017-03-14 | 2017-03-15 | 6 rounds with each 2 hours (constraint of tool, does not allow to run 1 round 12 hours), Monitor hardware usage, Collect report between loads.
12 | Analyse, report | 2 | Senior Tester | 2017-03-16 | 2017-03-16 | Final test report available after fixing issues
|  | 124 | Senior Tester
|  | 16.8 | Test Leader
|  | 26 | Nam